## can u give different names for
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a user, I want to submit a support request in natural language so that a service ticket can be created automatically. | MUST HAVE | None | Rahul | 3- Completed
Sprint 1 | Sprint 2 | US-02 | As a system, I want to clean and normalize user input text so that it can be processed accurately. | MUST HAVE | None | Laya | 3- Completed
Sprint 1 | Sprint 1 | US-03 | As a system, I want to assign priority levels to tickets so that critical issues are handled first. | SHOULD HAVE | US-03 | Lasya | 1- Not Started
Sprint 1 | Sprint 1 | US-04 | As a system, I want to classify tickets into predefined categories based on the user input. | MUST HAVE | US-02 | Alekhya | 2- In Progress
Sprint 2 | Sprint 2 | US-05 | As a system, I want to detect user sentiment to prioritize frustrated customers. | SHOULD HAVE | US-02 | Vikram | 1- Not Started
Sprint 2 | Sprint 3 | US-06 | As a manager, I want a confidence score for each AI classification to ensure accuracy. | SHOULD HAVE | US-04 | Priya | 1- Not Started
Sprint 2 | Sprint 2 | US-07 | As a system, I want to route high-confidence tickets to an automated FAQ response. | SHOULD HAVE | US-04 | Arjun | 1- Not Started
Sprint 3 | Sprint 3 | US-08 | As a system, I want to route low-confidence tickets directly to a human agent. | MUST HAVE | US-04 | Sneha | 1- Not Started
Sprint 3 | Sprint 3 | US-09 | As an agent, I want to see the AI's "reasoning" for its category suggestion. | COULD HAVE | US-04 | Ishaan | 1- Not Started
Sprint 3 | Sprint 3 | US-10 | As a system, I want to extract order numbers and email addresses using NER. | MUST HAVE | US-02 | Kavya | 1- Not Started
Sprint 4 | Sprint 4 | US-11 | As a system, I want to detect the language of the ticket for proper routing. | SHOULD HAVE | None | Rahul | 1- Not Started
Sprint 4 | Sprint 4 | US-12 | As a user, I want my ticket translated into the support team's native language. | SHOULD HAVE | US-11 | Laya | 1- Not Started
Sprint 4 | Sprint 4 | US-13 | As a developer, I want to log agent corrections to the AI to build a feedback loop. | MUST HAVE | US-04 | Lasya | 1- Not Started
Sprint 5 | Sprint 5 | US-14 | As a system, I want to redact PII (SSN, credit card) from tickets for security. | MUST HAVE | US-02 | Alekhya | 1- Not Started
Sprint 5 | Sprint 5 | US-15 | As a system, I want to summarize long ticket threads for human agents. | SHOULD HAVE | US-02 | Vikram | 1- Not Started
Sprint 5 | Sprint 5 | US-16 | As a manager, I want an AI "Deflection Rate" report to measure ROI. | MUST HAVE | US-07 | Priya | 1- Not Started
Sprint 6 | Sprint 6 | US-17 | As a developer, I want to monitor for model drift every 24 hours to ensure quality. | SHOULD HAVE | None | Arjun | 1- Not Started
Sprint 6 | Sprint 6 | US-18 | As a system, I want to flag duplicate tickets from the same user automatically. | COULD HAVE | US-10 | Sneha | 1- Not Started
Sprint 6 | Sprint 6 | US-19 | As an agent, I want the AI to suggest three "next steps" based on the issue. | COULD HAVE | US-15 | Ishaan | 1- Not Started
Sprint 7 | Sprint 7 | US-20 | As a system, I want to check the internal Knowledge Base for existing solutions. | MUST HAVE | None | Kavya | 1- Not Started
Sprint 7 | Sprint 7 | US-21 | As a system, I want to version-control every model deployment for easy rollbacks. | SHOULD HAVE | None | Rahul | 1- Not Started
Sprint 7 | Sprint 7 | US-22 | As a system, I want to identify "VIP" customers via CRM integration. | SHOULD HAVE | US-10 | Laya | 1- Not Started
Sprint 8 | Sprint 8 | US-23 | As a user, I want a "thumbs up/down" button on AI automated responses. | MUST HAVE | US-07 | Lasya | 1- Not Started
Sprint 8 | Sprint 8 | US-24 | As a system, I want to handle image attachments using OCR for error messages. | COULD HAVE | None | Alekhya | 1- Not Started
Sprint 8 | Sprint 8 | US-25 | As an agent, I want the AI to draft an email reply that I can edit and send. | SHOULD HAVE | US-15 | Vikram | 1- Not Started
Sprint 9 | Sprint 9 | US-26 | As a manager, I want an alert if AI accuracy drops below the 80% threshold. | SHOULD HAVE | US-17 | Priya | 1- Not Started
Sprint 9 | Sprint 9 | US-27 | As a system, I want to link related tickets from different users together. | COULD HAVE | US-18 | Arjun | 1- Not Started
Sprint 9 | Sprint 9 | US-28 | As a developer, I want to implement safety guardrails for LLM-generated text. | MUST HAVE | US-25 | Sneha | 1- Not Started
Sprint 10 | Sprint 10 | US-29 | As a system, I want to detect "Spam" or "Bot" submissions automatically. | MUST HAVE | None | Ishaan | 1- Not Started
Sprint 10 | Sprint 10 | US-30 | As a manager, I want a dashboard showing Top 10 trending support topics. | SHOULD HAVE | US-04 | Kavya | 1- Not Started
Sprint 11 | Sprint 11 | US-31 | As a developer, I want to perform A/B testing on different classification models. | COULD HAVE | US-04 | Rahul | 1- Not Started
Sprint 11 | Sprint 11 | US-32 | As a system, I want to detect sarcasm to improve sentiment analysis scores. | COULD HAVE | US-05 | Laya | 1- Not Started
Sprint 11 | Sprint 11 | US-33 | As a user, I want a chatbot interface for real-time ticket status updates. | SHOULD HAVE | None | Lasya | 1- Not Started
Sprint 12 | Sprint 12 | US-34 | As a system, I want to extract trends from ticket attachments (PDF/Images). | COULD HAVE | US-24 | Alekhya | 1- Not Started
Sprint 12 | Sprint 12 | US-35 | As a system, I want to analyze "Time-to-Resolution" for AI vs Human tickets. | SHOULD HAVE | US-07 | Vikram | 1- Not Started
Sprint 12 | Sprint 12 | US-36 | As an agent, I want to "tag" tickets to help the AI learn new sub-categories. | COULD HAVE | US-13 | Priya | 1- Not Started
Sprint 13 | Sprint 13 | US-37 | As a user, I want to be informed if I am interacting with an AI agent. | MUST HAVE | None | Arjun | 1- Not Started
Sprint 13 | Sprint 13 | US-38 | As a developer, I want to load-test the AI API to handle 1000 requests/sec. | SHOULD HAVE | None | Sneha | 1- Not Started
Sprint 13 | Sprint 13 | US-39 | As a system, I want to suggest tags for tickets to help with archive searching. | SHOULD HAVE | US-04 | Ishaan | 1- Not Started
Sprint 14 | Sprint 14 | US-40 | As a manager, I want a heatmap of ticket volume by hour and day. | COULD HAVE | None | Kavya | 1- Not Started
Sprint 14 | Sprint 14 | US-41 | As a system, I want to route hardware-related tickets to the lab team. | SHOULD HAVE | US-04 | Rahul | 1- Not Started
Sprint 14 | Sprint 14 | US-42 | As a user, I want the AI to remember context from my tickets in the last 30 days. | SHOULD HAVE | US-10 | Laya | 1- Not Started
Sprint 15 | Sprint 15 | US-43 | As a system, I want to evaluate the readability of AI-generated responses. | COULD HAVE | US-25 | Lasya | 1- Not Started
Sprint 15 | Sprint 15 | US-44 | As a manager, I want a monthly audit report on AI decision accuracy. | SHOULD HAVE | US-16 | Alekhya | 1- Not Started
Sprint 15 | Sprint 15 | US-45 | As a system, I want to detect if a user is "churn-risk" based on ticket history. | SHOULD HAVE | US-05 | Vikram | 1- Not Started
Sprint 16 | Sprint 16 | US-46 | As an agent, I want to see a "Top Similar Tickets" sidebar when working. | COULD HAVE | US-18 | Priya | 1- Not Started
Sprint 16 | Sprint 16 | US-47 | As a system, I want to automatically categorize tickets into Jira/Trello tasks. | SHOULD HAVE | US-04 | Arjun | 1- Not Started
Sprint 16 | Sprint 16 | US-48 | As a developer, I want to implement a weekly data backup for training sets. | MUST HAVE | US-13 | Sneha | 1- Not Started
Sprint 17 | Sprint 17 | US-49 | As a user, I want to give voice-to-text input for my support requests. | COULD HAVE | None | Ishaan | 1- Not Started
Sprint 17 | Sprint 17 | US-50 | As a manager, I want a prediction of next week's ticket volume via AI. | COULD HAVE | US-40 | Kavya | 1- Not Started